PROJECT MANAGEMENT ASSIGNMENT

Tourism Project (Academic Purpose)

Conducting a Hospitality Skills Awareness Workshop

for Local Tourism Stakeholders — Arugam Bay, Ampara District

Project Title Option No. 8

Course: Project Management  |  Programme: THM (2324)

Submission Deadline: 16.07.2026

# 1. Project Title

Conducting a Hospitality Skills Awareness Workshop for Local Tourism Stakeholders in Arugam Bay, Ampara District.

# 2. Selected Project Place / Location

The project will be conducted at a community hall in Arugam Bay, Ampara District — one of Sri Lanka's premier coastal and surfing destinations. The location is chosen for its high concentration of small-scale tourism service providers, including guest house owners, restaurant staff, tuk-tuk drivers, surf instructors and boutique operators, who directly interact with domestic and international visitors. The venue is central, easily accessible and suitable for a one-day workshop of around 50 participants. (Final location to be approved by the lecturer.)

# 3. Background and Justification

Arugam Bay is one of the most popular coastal and surfing destinations in Sri Lanka and the leading tourist attraction in the Ampara District. It draws a steady flow of domestic and international visitors, particularly during the surf season from around April to October. Tourism is the main source of income for a large part of the local community, which operates small guest houses, restaurants, cafés, surf schools, transport services and handicraft stalls.

Despite this dependence on tourism, many frontline workers have never received any formal hospitality or customer-service training. Skills are usually learned informally on the job, and standards therefore vary widely between businesses. Common gaps include weak communication with foreign guests, inconsistent hygiene and food-safety practices, limited awareness of guest safety, and a lack of professional service etiquette. These gaps can lower visitor satisfaction, reduce positive online reviews and repeat visits, and ultimately weaken the livelihoods of the community that depends on tourism.

This project addresses that gap by organising a short, practical Hospitality Skills Awareness Workshop for local tourism stakeholders. The workshop delivers focused awareness on service quality, professional communication, cleanliness, food safety and guest handling, so that participants can immediately apply improved practices in their day-to-day work. Because it is a one-day, community-based event with a modest budget, the project is realistic, low-cost and achievable within a short period. At the same time it requires the group to apply the full range of project management functions and management roles, making it well suited to this academic assignment.

# 4. Project Aim and Objectives

## Aim

To improve the hospitality and customer-service skills of local tourism stakeholders in Arugam Bay through a one-day awareness workshop, thereby enhancing the overall visitor experience in the Ampara District.

## Objectives

- To raise awareness among at least 50 local tourism stakeholders on core hospitality and customer-service standards.

- To conduct practical sessions on communication, guest handling, hygiene and safety.

- To distribute simple reference materials that participants can use after the workshop.

- To apply project management functions and management roles in planning and delivering the event within budget and on schedule.

- To evaluate participant satisfaction and skill awareness through a short feedback survey.

# 5. Starting Date and Ending Date

Project Starting Date: 01 September 2026 (planning and preparation begins)

Workshop / Event Date: 10 October 2026 (one-day workshop)

Project Ending Date: 15 October 2026 (evaluation and final reporting completed)

Total project duration: approximately six weeks.

# 6. Project Scope

## In Scope

- Planning, organising and delivering one full-day hospitality skills awareness workshop for around 50 local tourism stakeholders.

- Arranging venue, resource persons, training materials, refreshments and certificates of participation.

- Marketing and registering participants, and collecting post-workshop feedback.

## Out of Scope

- Long-term or accredited vocational certification programmes.

- Infrastructure development, financial grants, or ongoing mentoring beyond the workshop day.

- Projects outside the selected Arugam Bay location.

# 7. Project Team Structure and Work Roles

The project is carried out by the following student group, with each member assigned a specific management responsibility to ensure effective teamwork and accountability.

| Index No. | Name | Work Role | Key Responsibilities |
| --- | --- | --- | --- |
| AMP/THM/2324/F/07 | M.A. Hasan Mahmood | Project Manager | Leads the team, sets objectives, coordinates activities, monitors progress and ensures on-time delivery. |
| AMP/THM/2324/F/034 | Kishanth | Finance Coordinator | Prepares and controls the budget, tracks expenses, manages funds and keeps financial records. |
| AMP/THM/2324/F/45 | F. Sajath Ahamed | Logistics Coordinator | Arranges venue, seating, equipment, transport and refreshments for the workshop. |
| AMP/THM/2324/F/59 | M.S.M. Hassaan | Marketing Officer | Promotes the event, designs flyers/social posts and manages participant registration. |
| AMP/THM/2324/F/203 | H.M. Risni | Event Coordinator | Plans the agenda, liaises with resource persons and manages event flow on the day. |
| AMP/THM/2324/F/210 | K. Kajanan | Risk Coordinator | Identifies risks, prepares mitigation plans and manages health, safety and contingencies. |
| AMP/THM/2324/F/225 | V. Vinotharshan | Documentation Officer | Maintains records, prepares the final report and certificates. |
| AMP/THM/2324/F/226 | T. Sanjey | Monitoring Officer | Tracks progress against the plan, collects feedback and evaluates outcomes against objectives. |
| AMP/THM/2324/F/229 | M. Zaheer | Media & Community Liaison Officer | Handles photography and media coverage and coordinates with the local community and stakeholders. |

# 8. Application of Project Management Functions

## Planning

Planning is the foundation of the project. The team defines clear objectives, sets a target of at least 50 participants, and prepares the work breakdown structure, six-week timeline and estimated budget. During this stage the group identifies a suitable venue, confirms the resource persons who will deliver the sessions, decides the content of each session, and plans the training materials, refreshments and certificates. A simple feedback method is also designed in advance so that outcomes can be measured. Responsibilities are documented so every member knows exactly what to prepare and by when.

## Organizing

In the organising stage, resources are arranged and roles are allocated to match each member's responsibility. The Logistics Coordinator secures the community hall, seating and audio-visual equipment; the Finance Coordinator organises and releases the budget; the Marketing Officer arranges promotion and registration; and the Event Coordinator structures the workshop agenda and liaises with the trainers. Tasks are sequenced so that promotion, registration and material preparation are all complete before the workshop day, avoiding last-minute pressure and ensuring resources are used efficiently.

## Leading

Leading keeps the team motivated and aligned. The Project Manager guides the group, holds short weekly check-in meetings, delegates tasks fairly and resolves any conflicts or delays quickly. By encouraging open communication and recognising members' contributions, the Project Manager maintains morale and keeps everyone focused on the shared goal throughout the six weeks. Good leadership also extends to the workshop day itself, where the team must welcome participants warmly and manage the sessions confidently.

## Controlling

Controlling ensures the project stays on track. Progress is measured against the timeline and budget at each weekly meeting. The Monitoring Officer tracks task completion against the WBS, the Finance Coordinator compares actual spending with the budget, and corrective action is taken whenever an activity falls behind or a cost rises. On the day, attendance is recorded against the target, and after the workshop the feedback survey is analysed to confirm that the objectives were achieved and to capture lessons for future events.

# 9. Management Roles Applied in the Project

Based on Mintzberg's management roles, the team applied the three categories as follows:

| Category | Role | How it was applied |
| --- | --- | --- |
| Interpersonal | Figurehead / Leader / Liaison | The Project Manager represents the team, leads members, and the Marketing & Event Coordinators liaise with stakeholders, resource persons and the community. |
| Informational | Monitor / Disseminator / Spokesperson | The Monitoring Officer gathers progress information, the Documentation Officer shares it internally, and the Project Manager acts as spokesperson to outside parties. |
| Decision-Making | Entrepreneur / Disturbance Handler / Resource Allocator / Negotiator | The team initiates the project, the Risk Coordinator handles problems, the Finance Coordinator allocates resources, and the Logistics Officer negotiates venue and supplier terms. |

# 10. Activity Plan / Work Breakdown Structure (WBS)

| WBS | Main Task | Sub-Activities |
| --- | --- | --- |
| 1.0 | Initiation & Planning | Approve topic; define objectives; assign roles; prepare plan and budget. |
| 2.0 | Logistics & Venue | Book community hall; arrange seating, equipment, transport and refreshments. |
| 3.0 | Marketing & Registration | Design flyers; promote on social media; register ~50 participants. |
| 4.0 | Content & Materials | Confirm resource persons; prepare slides, handouts and certificates. |
| 5.0 | Workshop Delivery | Conduct sessions on service, communication, hygiene and safety; practical activities. |
| 6.0 | Monitoring & Evaluation | Collect feedback; evaluate outcomes; prepare and submit final report. |

## Workshop-Day Agenda (10 October 2026)

To make delivery practical, the one-day workshop follows the structured agenda below.

| Time | Session | Responsible |
| --- | --- | --- |
| 8.30 – 9.00 | Registration and welcome | Marketing & Documentation Officers |
| 9.00 – 9.30 | Opening remarks and objectives | Project Manager |
| 9.30 – 11.00 | Customer service & professional communication | Resource Person 1 |
| 11.00 – 11.15 | Tea break | Logistics Coordinator |
| 11.15 – 12.45 | Hygiene, food safety and guest safety | Resource Person 2 |
| 12.45 – 1.30 | Lunch | Logistics Coordinator |
| 1.30 – 3.00 | Practical role-play & guest-handling activities | Event Coordinator |
| 3.00 – 3.45 | Feedback survey and certificates | Monitoring & Documentation Officers |
| 3.45 – 4.00 | Closing | Project Manager |

# 11. Project Timeline / Gantt Chart

The six-week schedule below shows how the main activities overlap from planning to closure. Shaded cells indicate the weeks in which each activity is active.

| Activity | W1 | W2 | W3 | W4 | W5 | W6 |
| --- | --- | --- | --- | --- | --- | --- |
| Planning & approvals |  |  |  |  |  |  |
| Venue & logistics booking |  |  |  |  |  |  |
| Marketing & registration |  |  |  |  |  |  |
| Resource & material prep |  |  |  |  |  |  |
| Workshop delivery |  |  |  |  |  |  |
| Monitoring & evaluation |  |  |  |  |  |  |
| Reporting & closure |  |  |  |  |  |  |

# 12. Estimated Budget

The estimated budget for the one-day workshop for approximately 50 participants is shown below. Amounts are indicative and in Sri Lankan Rupees (LKR).

| No. | Item | Details | Cost (LKR) |
| --- | --- | --- | --- |
| 1 | Venue hire | Community hall for one day | 15,000 |
| 2 | Resource persons | Honorarium for 2 trainers | 20,000 |
| 3 | Printing & materials | Handouts, banners, certificates | 12,000 |
| 4 | Refreshments | Tea + lunch for 50 participants | 25,000 |
| 5 | Marketing | Flyers & social media promotion | 5,000 |
| 6 | Equipment | Projector, sound system rental | 8,000 |
| 7 | Contingency | ~10% for unexpected costs | 9,000 |
|  | TOTAL |  | 94,000 |

# 13. Risk Analysis and Solutions

| Risk | Likelihood | Impact | Mitigation / Solution |
| --- | --- | --- | --- |
| Low participant turnout | Medium | High | Early promotion, confirmed pre-registration and reminder calls. |
| Bad weather on event day | Medium | Medium | Indoor venue booked; keep a backup date ready. |
| Budget overrun | Low | Medium | Maintain contingency fund; seek sponsorships; control spending. |
| Resource person unavailable | Low | High | Confirm early; arrange a backup trainer. |
| Poor engagement / language barrier | Medium | Medium | Use local language, practical demos and interactive activities. |

# 14. Expected Outcomes and Benefits

- At least 50 local tourism stakeholders gain improved awareness of hospitality and customer-service standards.

- Better guest handling, communication and hygiene practices among frontline workers in Arugam Bay.

- Enhanced visitor satisfaction, supporting repeat tourism and community livelihoods.

- Strengthened teamwork and practical project management experience for the student group.

- A reusable workshop model that can be repeated in other tourist areas of the Ampara District.

# 15. Conclusion and Recommendations

The Hospitality Skills Awareness Workshop is a realistic, low-cost and achievable short-term tourism project for Arugam Bay in the Ampara District. It targets a genuine local need — the lack of formal hospitality training among frontline tourism workers — and responds with a focused one-day event that the student group can plan and deliver within six weeks on a modest budget. Through clear planning, organised teamwork, strong leadership and careful control of time and cost, the group can improve the service quality of local stakeholders and enhance the overall visitor experience.

The project also clearly demonstrates the academic learning outcomes of the course. Each of the four project management functions — planning, organising, leading and controlling — is applied at a specific stage, and Mintzberg's interpersonal, informational and decision-making roles are distributed across the team so that every member gains hands-on management experience.

It is recommended that similar awareness workshops be conducted regularly and extended to other tourist locations in the district such as Pottuvil and Panama, that local tourism authorities, hotels and businesses support these initiatives through sponsorship and resource persons, and that a short follow-up survey be carried out a few weeks after the event to measure the longer-term impact of the training on service quality and visitor satisfaction. With minor adjustments, the same model can be scaled up into a recurring capacity-building programme for the Ampara tourism sector.